## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | US 01 | Registration of buyer and seller providiing correct details | MUST HAVE | 8 |  | 3- Completed
1 | 1 | US 01 | Buyer and seller shold be able to login to their account if it is active | MUST HAVE | 8 |  | 3- Completed
1 | 1 | US 01 | Buyer should be able to activate and deactivate their account | COULD HAVE | 8 |  | 3- Completed
1 | 1 | US 01 | Seller should also be able to remove their account by making it inactive | COULD HAVE | 5 |  | 3- Completed
1 | 1 | US 01 | Buyer request for accessing cart and wishlist should be permitted | MUST HAVE | 8 |  | 3- Completed
1 | 1 | US 02 | Seller should be able to add and remove product | MUST HAVE | 5 |  | 3- Completed
1 | 1 | US 02 | As a visitor I should be able to see all the products and able to search product based on category and product name | MUST HAVE | 5 |  | 3- Completed
| 1 | US 02 | Buyer should be able to Add, Remove and Move products from wishlist to cart using US Ms 01 | MUST HAVE | 5 |  | 3- Completed
1 | 1 | US 03 | Buyer and seller should be able to add and remove products from cart and place an order | MUST HAVE | 8 |  | 3- Completed
1 | 1 | US 03 | Buyer can view all the orders placed | MUST HAVE | 5 |  | 3- Completed
1 | 1 | US 03 | Buyer should reoreder | COULD HAVE | 5 |  | 3- Completed
Note on F1: Kindly refrain from providing more than 8 points to user stories
Note on F2: Kindly refrain from providing more than 8 points to user stories

## Sprint I Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 39 | 20.5 | 18.5 | 0
SPRINT 1 BACKLOG
US-01 | T1 | Creating maven project and add dependencies | 2020-12-07 | 2020-12-07 | 1103067 | Build | 3- Completed | 2 | 1 | 1 | 0
| T2 | Managing source code with Git and publishing final build using maven | 2020-12-07 | 2020-12-07 | 1103067 | Coding | 3- Completed | 1 | 0.5 | 0.5 | 0
| T3 | Configuring JPA and creating JPA repository | 2020-12-07 | 2020-12-07 | 1103067 | Coding | 3- Completed | 3 | 1.5 | 1.5 | 0
| T4 | Creating DTO and entity class | 2020-12-07 | 2020-12-07 | 1103067 | Coding | 3- Completed | 1 | 0.5 | 0.5 | 0
| T5 | Creating service class | 2020-12-07 | 2020-12-08 | 1103067 | Coding | 3- Completed | 3 | 1.5 | 1.5 | 0
| T6 | Creating controller class | 2020-12-08 | 2020-12-08 | 1103067 | Coding | 3- Completed | 2 | 1 | 1 | 0
| T7 | Testing it through postman | 2020-12-08 | 2020-12-08 | 1103067 | Unit Test | 3- Completed | 2 | 1 | 1 | 0
US-02 | T1 | Creating maven project and add dependencies | 2020-12-07 | 2020-12-07 | 1103122 | Build | 3- Completed | 3 | 2.5 | 0.5 | 0
| T2 | Managing source code with Git and publishing final build using maven | 2020-12-07 | 2020-12-08 | 1103122 | Coding | 3- Completed | 2 | 1 | 1 | 0
| T3 | Create DAO class | 2020-12-08 | 2020-12-08 | 1103122 | Coding | 3- Completed | 1 | 0.5 | 0.5 | 0
| T4 | Create DTO and entity class | 2020-12-08 | 2020-12-09 | 1103122 | Coding | 3- Completed | 2 | 1 | 1 | 0
| T5 | Create service class | 2020-12-09 | 2020-12-09 | 1103122 | Coding | 3- Completed | 3 | 1.5 | 1.5 | 0
| T6 | Testing through postman | 2020-12-09 | 2020-12-09 | 1103122 | Unit Test | 3- Completed | 2 | 1 | 1 | 0
Us-03 | T1 | Creating maven project and add dependencies | 2020-12-07 | 2020-12-07 | 1103090 | Build | 3- Completed | 2 | 1 | 1 | 0
| T2 | Managing source code with Git and publishing final build using maven | 2020-12-07 | 2020-12-07 | 1103090 | Coding | 3- Completed | 1 | 0.5 | 0.5 | 0
| T3 | Create DAO class | 2020-12-08 | 2020-12-08 | 1103090 | Coding | 3- Completed | 3 | 1.5 | 1.5 | 0
| T4 | Create DTO and entity class | 2020-12-08 | 2020-12-08 | 1103090 | Coding | 3- Completed | 1 | 0.5 | 0.5 | 0
| T5 | Create service class | 2020-12-09 | 2020-12-09 | 1103090 | Coding | 3- Completed | 3 | 1.5 | 1.5 | 0
| T6 | Testing through postman | 2020-12-09 | 2020-12-09 | 1103090 | Unit Test | 3- Completed | 2 | 1 | 1 | 0
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work

## Sprint II Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-01 | T1 | Project Configuration | 2020-12-10 | 2020-12-10 | 1103067 | Unit Test | 3- Completed
| T2 | Minor Enhancement | 2020-12-07 | 2020-12-10 | 1103067 | Coding | 3- Completed
US-02 | T1 | Project Configuration | 2020-12-10 | 2020-12-10 | 1103122 | Unit Test | 3- Completed
| T2 | Minor Enhancement | 07-Dec-202 | 2020-12-10 | 1103122 | Coding | 3- Completed
US-03 | T1 | Project Configuration | 2020-12-10 | 2020-12-10 | 1103090 | Unit Test | 3-Completed
| T2 | Minor Enhancement | 2020-12-07 | 2020-12-10 | 1103090 | Coding | 3-Completed
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work

## Retrospection
Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
2020-12-07 | 2020-12-09 | Sujala | Create microservice of US01 | Removing the unused imports | Start adding comments for the code | Complete user story 1
2020-12-07 | 2020-12-09 | Sanjay | Create microservice of US02 | Don’t make it complex | Start giving correct status code | Complete user story 2
2020-12-07 | 2020-12-09 | Vaishnavi | Create microservice of US03 | Removing the unused imports | Maintain backend for easy access of data | Complete user story 3

## Product Backlog Grooming
Sprint | US ID | Points Discussed
1 | US 01 | which user story to be implemented by whom
1 | US 01 | implemented backend for US 01
1 | US 01 | test through postman
1 | US 02 | implemented backend for US 02
1 | US 02 | testing through postman
1 | US 02 | Implemented backend for Us 03
1 | US 03 | test through postman

## Stand up Meeting
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken
1 | US01,US02,US03 | 1 | 1103067, 1103122, 1103090 | Which user story to be implemented by whom | fixed | completed
1 | US01 | 1 | 1103067, 1103122, 1103090 | implement backend of us01 | done | completed
1 | US02 | 1 | 1103067, 1103122, 1103090 | implemented backend of us02 | done | completed
1 | US03 | 1 | 1103067, 1103122, 1103090 | implement backend of us03 | done | completed
1 | US01 | 2 | 1103067, 1103122, 1103090 | Contacted with the assignee of US 1 & 2 for the end points | done | completed
1 | US01 | 2 | 1103067, 1103122, 1103090 | Error solving, checking end point | done | completed
1 | US02 | 2 | 1103067, 1103122, 1103090 | Contacted with the assignee of US 1 & 2 for the end points | done | completed
1 | US02 | 2 | 1103067, 1103122, 1103090 | Error solving, checking end point | done | completed
1 | US03 | 2 | 1103067, 1103122, 1103090 | Contacted with the assignee of US 1 & 2 for the end points | done | completed
1 | US03 | 2 | 1103067, 1103122, 1103090 | Error solving, checking end point | done | completed
2 | US01 | 3 | 1103067, 1103122, 1103090 | Cloud Implementation, Sonar Cloud report Generation | done | completed
2 | US02 | 3 | 1103067, 1103122, 1103090 | Cloud Implementation, Sonar Cloud report Generation | done | completed
2 | US03 | 3 | 1103067, 1103122, 1103090 | Cloud Implementation, Sonar Cloud report Generation | done | completed
2 | US01 | 4 | 1103067, 1103122, 1103090 | Testing with postman | done | completed
2 | US02 | 4 | 1103067, 1103122, 1103090 | Testing with postman | done | completed
2 | US03 | 4 | 1103067, 1103122, 1103090 | Testing with postman | done | completed